ANNEX 5

Work plan mental health 2015-2017

| 1 | Objective Strengthen effective leadership and management for mental health care (GGZ) |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Activity(ies Tasks Responsible party Period Budget |  |  |  |  |
| 1.1 | Adjustment of the national plan for mental health care so that it is in line with the national and international plans and conventions | Draw up a draft action plan Discuss draft action plan with stakeholders Adjust draft plan and budgeting Finalize plan and submit to the Minister of Public Health and other relevant ministries and organisations | MOH | 1st quarter 2015 | 20,000 |
| 1.2 | Adjust the current law and bill for mental health care so that it meets the CRPD3 and other international (human rights) conventions | Formulate a bill Discuss bill with all stakeholders Submit bill to the National Assembly Publish the act | MOH and PAHO | T quarter 2015 - 4th quarter 2017 | 15,000 |
| 1.3 | Establish a national and interdepartmental commission (inter-ministerial) for the promotion of mental health care and the prevention of mental illnesses | Write communications plan and policy brief Draw up TOR Lobby with the highest management MOH recruiting committee members Draw up and submit proposal for Council of Ministers Appoint committee Facilitate meetings of committee | MOH and all ministries | T quarter 2015-46 quarter 2017 | 12,000 |
| 1.4 | Adjust laws and legislation and policies within other ministries in such a manner that it takes into account the rights of | Review relevant legislation Make adjustments where necessary Discuss amendments to the law with all relevant | MOH, MinJusPol, MinATM, MinSoZaVo | 4th quarter 2015-46 | 35,000 |

Convention for the Rights of Persons with Disabilities

|  | Persons with a mental illness and promotes the mental health of the population in general and for persons with a mental affliction in particular | Stakeholders Submit amendments to the National Assembly Have amendments published |  | quarter 2017 |  |
| --- | --- | --- | --- | --- | --- |
| 1.5 | Facilitate a platform of patient associations of people having a mental health problem | Inventory which groups there are Offer the opportunity to persons with a mental health problem to start a patient association or an interest group by offering them support Call groups together Agree on consultation form and structure Formalise tasks Facilitate meetings | MOH, ADEKUS (psychology major) | 3rd quarter 2015-46 quarter 2017 | 10,000 |
| 1.6. | Establish a trust institution for people with a mental health affliction | Draw up a profile for this institution Study and establish legal framework | MOH and MinJuspol | 3rd quarter 2015-16 quarter 2017 | 5,000 |

| 2 | Objective: mental health care is accessible to all people in Suriname |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Activity | Tasks | Responsible party | Period | Budget |
| 2.1 | Make arrangements to provide mental health care also outside of PCS | Inventory which type of care can be provided outside of PCS, where, how, and by whom (15,000) Make agreements with the institutions how the care will be delivered (cooperation agreements, covenants) (5,000) Facilitate institutions to deliver that care by means of adjusting the infrastructure, training of personnel and providing guidelines by means of protocols (115,000) Establish forms of consultation between psychiatrists and psychologists and general practitioners, if necessary multidisciplinary teams (10,000) | PCS, SVPO en VMS/RGD/MZ | 3rd quarter 2015-4th quarter 2017 | 145,000 |
| 2.2 | Expand and strengthen personnel working in mental health care | Have a human resource needs assessment carried out for the GGZ with concrete actions plans and recommendations for reorganisation, training and recruitment and selection. | MOH , MinATM | 2nd quarter 2015-4th quarter 2015 | 20,000 |
|  |  | Provide training to staff working in the mental health care sector on the basis of gaps found through above study | PCS, ADEKUS, MOH, SVPO, FMEW, COVAB | L quarter 2016-4th quarter 2017 | 25,000 |
|  | Adjust curricula of existing courses | Screen curricula existing courses Minov | MOH, COVAB, PCS, SVPO, FMEW and | 3rd quarter 2015-3rd quarter 2016 | 15,000 |

Opleiden psychologen	| ADEKUS

| 2.3 | Financial accessibility to mental health assistance | With insurance companies and professional groups agree on the need for adjusting the number of sessions allowed with psychologists and psychiatrists | Social workers, MOH, Department of Psychiatry, SVPO | 3rd quarter 2015-4th quarter 2016 |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Compensate sessions with social workers | Social workers, MOH, Department of Psychiatry, SVPO | 3rd quarter 2015-4th quarter 2016 |  |
|  |  | Enter into discussions with insurance companies and the persons paying for health care and the Min of Justice and Police about “decriminalizing” suicide and addiction, so that these can be compensated by health insurance | Social workers, MOH, Department of Psychiatry, SVPO | 3rd quarter 2015-4th quarter 2016 |  |

| 3 | Objective: improve mental health (wellbeing) and prevent mental health afflictions van psychische aandoeningen |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Activity(ies) | Tasks | Responsible party |  | Period | Budget |  |
| 3.1 | Promote the importance of mental health and create understanding for (persons with) mental health afflictions | Screen existing health promotion campaigns and ascertain with the organisations where and how mental health and mental health care can be integrated in this | MOH | 3rd quarter 2015-46 quarter 2016 |  |  | 5,000 |
|  |  | On the basis of sound research into attitudes about mental health afflictions draw up a communications plan for a national anti-stigma and discrimination campaign and mental health awareness campaign through different media | MOH | 3rd quarter 2015 - 3rd quarter 2017 |  |  | 250,000 |
|  |  | Draw up social guide and publish it about where one can go for mental health care, but also with elaborate information about what mental health is and what mental health afflictions are | MOH and institutions | le quarter 2016 - 3rd quarter 2016 |  |  | 50,000 |
| 3.2 | National policy and activities to have children grow up in a child-friendly surrounding and to prevent child abuse | Set up national network to prevent child abuse Support knowledge centre to prevent child abuse Develop educational programmes and tests Work with prenatal polyclinics and Cbs to give educational advice and course to (future) parents Information campaigns about conscious parenthood | MOH, PREKIMI, BOG, ADEKUS | 2nd quarter 2015 - 4th quarter 2017 |  |  | 150,000 |

| 3.3 | National policy and activities to prevent suicide | Set up a national network and knowledge centre to prevent suicide Legislation on suicide amended in the penal code Talk with insurance companies about the medical compensation of suicide Develop and carry out activities to prevent suicide | SUSUPREV and MOH, ADEKUS | 2nd quarter 2015 - 4th quarter 2017 | 100,000 |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Strengthen addiction care | Carry out a study into social determinants of addiction Develop interventions to anticipate on those determinants Adjust information and education from alcohol and drug addiction programme of PCS based on this study | PCS and NGOs | 2nd quarter 2015 - 4th quarter 2016 |  | 200,000 |
| 3.6 | Improve 24 hours (emergency) shelter and assistance to people in a mental health crisis | Evaluate and improve the crisis emergency line of PCS and establish other points and methods for crisis aid and assistance | PCS, RGD, MZ | 2nd quarter 2015-36 quarter 2016 |  | 250,000 |

| 4 | Objective: improve the date collection and research of GGZ and promote studies in mental health care |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Activity(ies) |  | Tasks |  | Responsible party | Period | Budget |
| 4.1 | Integrate GGZ data in the NHIS | 4.1.1 | Identify basic MH indicators to be incorporated into existing health information system (m.b.v. Global mental health observatory) | MOH, ADEKUS |  | 3rd quarter 2015-lst quarter 2016 |  |
|  |  | 4.1.2 | Development of forms for data collection | MOH, ADEKUS |  | lst quarter 2016-2nd quarter 2016 | 10,000 |

|  |  | 4.1.3 | Train health workers to routinely collect data | MOH, ADEKUS | 2nd quarter 2016-4th quarter 2016 | 25,000 |
| --- | --- | --- | --- | --- | --- | --- |
| 4.2 | Monitor and evaluate the NMHP | 4.2.1 | Draw up M&E plan | MOH and PAHO and ADEKUS | 3rd quarter 2015-1st quarter 2016 | 15,000 |
| 4.4 | Promotion of mental health research | 4.4.1 | Identify possibilities and interests to develop research initiatives in the mental health field | MOH, PCS, BOG, PREKIMI, SUSUPREV, SVPO, regional organisations, ADEKUS | 3rd quarter 2016 and ongoing | 150,000 |
|  |  | 4.4.2 | Identify potential topics for research |  |  |  |
|  |  | 4.4.3 | Search for partners at national level, in the Caribbean or in other regions |  |  |  |